## Sheet1
PT8612 Project Plan

Task	Duration	Resources
PCB Manufactoring	2-3 weeks	None
PCB Mounting	1-2 weeks	None
Partlist	2 days	GBG
Documentation for production	2 days	XW

Schematics PSU	2 days	XW
Schematics Clock System	1 week	XW,THH
Schematics Level Detector	1 week	GBG,XW

Cooling	1 week	THH